## Slide 1
Zycus - UniSan S2P Implementation
Project Status Update
As of 2026-10-01

## Slide 2
Where we are
40.6%
of project tasks complete
116 of 286 tasks delivered
Chart: 
| Delivered | Remaining
Task completion | 116 | 170
Overall status
Below target pace — recovery actions in progress
Currently in progress
Training Phase I
Hypercare Phase I
Configuration Validation & Documentation
eProc and eInvoice and Merlin APSD
Contract Management with Basic Setup
Supplier Information Management with In…

## Slide 3
Project timeline
Jun '26
Jul '26
Aug '26
Sep '26
Oct '26
Today
Training Phase I
Go /No-go Check Point ( Meeting with UniSan) f…
Release Zycus system to all users for iContra…
Production Go-Live Phase I
Hypercare Phase I
Supplier Information Management with Integrati…
Configuration Validation & Documentation
eProc and eInvoice and Merlin APSD
Contract Management with Basic Setup
iSource Configuration
Merlin Intake Configuration
Value KPI Sign-off
User Acceptance Testing (UAT) Phase II
Training Phase II
Production Migration Phase II
2026-05-19
2026-10-01
Completed
In progress
Upcoming
+ 13 earlier phase(s) completed — full history available on request.

## Slide 4
What's been delivered
Contract Sign Off
Project Initiation and Data Gathering
Configuration Validation & Documentation
Single Sign On and User details Integration
Contract Management with Basic Setup
Supplier Information Management with Integrat…
User Acceptance Testing (UAT) Phase I
UAT Completion I
Value KPI Sign-off
Training Completion
Production Migration Phase I
KPI Reports to be migrated on PROD
Sanity on Production for iContract and iSuppl…
Go /No-go Check Point ( Meeting with UniSan)…
+ 2 more phases delivered

## Slide 5
What we need from you
UniSan to review and Sign-off IAD Draft
Due 2026-07-21
UniSan to provide historical contracts details for Bulk Upload
Due 2026-07-16
UniSan to review uploaded details and provide go ahead for bulk upload into P…
Due 2026-07-24
UniSan to provide feedback
Due 2026-07-22
UniSan to provide supplier bulk upload data in the template provided by Zycus…
Due 2026-06-12
UniSan to provide updated bulk upload data
Due 2026-06-24
UniSan to review bulk uploaded data
Due 2026-07-01
UniSan to sign off on supplier bulk upload
Due 2026-07-01
+ 2 further item(s) — details shared separately.

## Slide 6
What's next
Upcoming phase
iSource Configuration
Target: 2026-08-06
Thank you for your continued partnership. We look forward to the next milestone together.