## Slide 1
Zycus - Titan S2P Implementation
Project Status Update
As of 2026-08-01

## Slide 2
Where we are
56.6%
of project tasks complete
207 of 366 tasks delivered
Chart: 
| Delivered | Remaining
Task completion | 207 | 159
Overall status
Below target pace — recovery actions in progress
Currently in progress
Build
Migration
Hypercare
Configuration Documentation workshop

## Slide 3
Project timeline
Feb '26
Apr '26
Jun '26
Aug '26
Oct '26
Dec '26
Today
Build
Project Initiation & Data Gathering
Migration
TTT
Go Live
Hypercare
Configuration Documentation workshop
Configuration and Build phase
User Acceptance Testing (UAT)
P2P Cutover
2026-01-28
2026-12-07
Completed
In progress
Upcoming

## Slide 4
What's been delivered
Project Initiation
Data Gathering
Requirement Workshop
UAT
TTT
Go Live
Project Initiation & Data Gathering

## Slide 5
What we need from you
Titan to provide sign off on Test Closure Memo
Due 2026-09-23
Titan to provide refreshed Master data for PRODUCTION
Due 2026-09-28

## Slide 6
What's next
Upcoming phase
Configuration and Build phase
Target: 2026-09-03
Thank you for your continued partnership. We look forward to the next milestone together.