## Slide 1
INTERNAL ONLY
Portfolio Health Review
Cross-project synthesis for Zycus leadership
2 projects • As of 2026-07-10
Portfolio of 2 active project(s); worst current status is Red. 1 at Red (Zycus - UniSan S2P Implementation). 1 at Amber (Zycus - Titan S2P Implementation).

## Slide 2
Portfolio snapshot
Independently computed RAG status per project
INTERNAL ONLY — Zycus leadership
AMBER
Zycus - Titan S2P Implementation
Schedule Green · 6.8% (10/148)
Milestone Amber · 14.3% of 14
Integrity Amber · 3 issue(s)
Comments logged
RED
Zycus - UniSan S2P Implementation
Schedule Red · 25.9% (44/170)
Milestone Amber · 5.1% of 39
Integrity Green · 0 issue(s)
Comments none logged

## Slide 3
Schedule slippage & milestone health
Earliest vs latest stored snapshot, per project
INTERNAL ONLY — Zycus leadership
Zycus - Titan S2P Implementation
8.1%
6.8% (-1.3 pts)
Zycus - UniSan S2P Implementation
27.1%
25.9% (-1.2 pts)
■ earliest ■ latest
Milestone weakness
Milestone health is Amber-or-worse across the entire portfolio — phase-level slippage is a shared weakness, not a one-project issue.
Zycus - Titan S2P Impleme…: Amber (14.3%) — Build, Migration
Zycus - UniSan S2P Implem…: Amber (5.1%) — Training Phase I, Hypercare Phase I

## Slide 4
Governance gap: commentary discipline
Stakeholder-comment logging by project
INTERNAL ONLY — Zycus leadership
Stakeholder-comment logging is inconsistent across projects — some PMs log commentary, others log none, which biases every comment-derived signal.
Zycus - Titan S2P Implementation
Comments logged
Zycus - UniSan S2P Implementation
No comments logged
Why it matters: every comment-derived signal (blockers, sentiment, data-integrity) is blind wherever a PM logs nothing — an absence of findings there is not evidence of health.

## Slide 5
Data quality: source-tool reliability
Where the source file's own status fields disagree with computed status
INTERNAL ONLY — Zycus leadership
The reliability of the source tool's own status fields varies by project — some files' self-reported health disagrees with the computed status more than others.
Zycus - Titan S2P Implementation 1 conflict(s)
Source file's own Schedule Health is 'Green', but this agent computed 'Amber' from independently verified signals.
Zycus - UniSan S2P Implementation 0 conflict(s)
Source status fields agree with computed status.

## Slide 6
Recommendations
Narrative: fallback-template
INTERNAL ONLY — Zycus leadership
1
Treat phase-level milestone slippage as a portfolio-wide problem and review phase re-baselining across projects, not case by case.
2
Standardise stakeholder-comment logging across PMs — uneven commentary discipline is silently biasing the comment-derived signals.
3
Audit source-file status fields where they diverge most from computed status before trusting any vendor-reported health number.